## project
Burndown Chart
[6 empty] | Period Highlight: |  |  |  |  | 14 |  | Plan |  |  | Actual |  |  |  | % Complete |  | Actual (beyond plan) | [5 empty] | % Complete (beyond plan)
| PLAN | PLAN | ACTUAL | ACTUAL | PERCENT
ACTIVITY | START | DURATION | START | DURATION | COMPLETE | PERIODS |  |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [7 empty] | Week 4
[6 empty] | Mon | Tue | Wed | Thurs | Fri | Sat | Sun |  | Mon | Tue | Wed | Thurs | Fri | Sat | Sun | Mon | Tue | Wed | Thurs | Fri | Sat | Sun |  | Mon | Tue | Wed | Thurs | Fri | Sat | Sun
Seed | Sprint 1 | 1hr
Board | Sprint 1 | 5hr
Player | Sprint 1 | 2hr
Game Manager | Sprint 1 | 5hr
GUI
Menus | Sprint 2 | 4hr
Getting Input | Sprint 2 | 4hr
Drawing Screen | Sprint 2 | 5hr
AI
Beginner | Sprint 2 | 1hr
Easy | Sprint 3 | 2hr
Medium | Sprint 3 | 4hr
Hard | Sprint 3 | 4hr
Client Server Remote Play | Sprint 3 | 4hr