## project
Burndown Chart
[6 empty] | Updated Sprint 1 and Sprint 2 | [6 empty] | Color Key |  |  | In Progress |  |  |  | Complete | M | Meeting Session Focus | [5 empty] | Planned Time
Planned Completion
| PLAN | PLAN | ACTUAL | ACTUAL | PERCENT
ACTIVITY | START | DURATION | START | DURATION | COMPLETE | PERIODS |  |  | Sprint 1 | [6 empty] | Sprint 2 | [6 empty] | Sprint 3 | [7 empty] | Sprint 3
[6 empty] | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 |  | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 |  | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
Seed | Sprint 1 | 1hr | Sprint 1 | 1 hr | 100% |  |  |  |  | M
Board | Sprint 1 | 5hr | Sprint 1 | 4 hr | 100% | [5 empty] | M
Player | Sprint 1 | 2hr | Sprint 1 | 1 hr | 100%
Game Manager | Sprint 1 | 5hr | Sprint 1 | 6 hr | 95% | [6 empty] | M
Kalah Main (updated) | Sprint 1 | 4 hr | Sprint 1 | 5 hr | 85%
GUI
Menus | Sprint 2 | 4hr | Sprint 2 |  | 0% | [12 empty] | M
Getting Input | Sprint 2 | 4hr | Sprint 2 |  | 0%
Drawing Screen | Sprint 2 | 5hr | Sprint 2 |  | 0% | [8 empty] | M
AI |  |  |  |  | 0%
Client Server Remote Play | Sprint 3 | 4hr | Sprint 2 |  | 0% | [13 empty] | M
Beginner | Sprint 2 | 1hr |  |  | 0%
Easy | Sprint 3 | 2hr |  |  | 0%
Medium | Sprint 3 | 4hr |  |  | 0%
Hard | Sprint 3 | 4hr |  |  | 0%