## project
Project Planner
[6 empty] | Period Highlight: |  |  |  |  | 14 |  |  |  | Plan |  |  | Actual |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
| PLAN | PLAN | ACTUAL | ACTUAL | PERCENT
ACTIVITY | START | DURATION | START | DURATION | COMPLETE | PERIODS |  |  | Jan | Feb |  |  |  | Feb | Mar |  |  |  | Mar | Apr |  |  |  | Apr | May |  |  |  | May
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Neil McHenry - Launch Controls | bar: PERIODS 1 to May 29; May 31; May 33; May 35; May 37; May 39; May 41
Research | 1 | 13 | 1 | 6 | 20% | bar: PERIODS 1 to Mar 13; Apr 15; Apr 17; Apr 19; May 21; May 23; May 25; May 27; May 31; May 33; May 35; May 37; May 39; May 41
Order Parts | 5 | 5 | 2 | 5 | 0% | bar: PERIODS 3; Feb 5 to Apr 15; Apr 17; Apr 19; May 21 to May 29; May 31; May 33; May 35; May 37; May 39; May 41
Program Logic | 4 | 3 | 4 | 6 | 0% | bar: PERIODS 1; PERIODS 3 to Feb 7; Feb 9 to Mar 13; Apr 15; Apr 17; Apr 19; May 21; May 23; May 25; May 27; May 29; May 31; May 33; May 35; May 37; May 39; May 41
Construct Control System | 8 | 7 | 4 | 8 | 0% | bar: PERIODS 1; PERIODS 3; Feb 5; Feb 7 to Apr 15; Apr 17; Apr 19; May 21; May 23; May 25; May 27; May 29; May 31; May 33; May 35; May 37; May 39; May 41
Interface Motors with BeagleBone | 7 | 4 | 12 | 5 | 0% | bar: PERIODS 1; PERIODS 3; Feb 5; Feb 7 to Apr 17; Apr 19; May 21; May 23; May 25; May 27; May 29; May 31; May 33; May 35; May 37; May 39; May 41
Create Closed Loop Feedback Scripts | 7 | 4 | 13 | 6 | 0% | bar: PERIODS 1; PERIODS 3; Feb 5; Feb 7 to Mar 11; Mar 13; Apr 15; Apr 17 to Apr 19; May 21; May 23; May 25; May 27; May 29; May 31; May 33; May 35; May 37; May 39; May 41
Assemble Weather Balloon Shelter | 10 | 7 | 13 | 18 | 0% | bar: Mar 10 to Apr 17; Apr 19; May 21; May 23; May 31 to May 42
Test & Improve Interop. of Sensors & Ctrls | 14 | 7 | 16 | 20 | 0% | bar: PERIODS 1; PERIODS 3; Mar 14 to May 21; May 23; May 25; May 27 to May 42
Implement Power System | 5 | 13 | 20 | 14 | 0% | bar: Feb 5 to Apr 17; Apr 19 to May 29; May 31; May 33; May 35; May 37; May 39 to May 42
Nhi Tran - Instrumentation
Research | 1 | 18 | 3 | 35 | 0% | bar: PERIODS 1 to Apr 18
Order Sensors | 2 | 5 | 17 | 5 | 0% | bar: PERIODS 2 to Feb 5
Interface Sensors with BeagleBone | 3 | 5 | 19 | 6 | 0% | bar: PERIODS 3 to Feb 6
Reduce Noise and Calibrate Sensors | 6 | 6 | 22 | 6 | 0% | bar: Feb 6 to Mar 11
Develop Control Algorithms | 9 | 6 | 29 | 8 | 0% | bar: Feb 9 to Mar 14
Test and Improve System Functionality | 15 | 7 | 36 | 6 | 0% | bar: Apr 15 to May 21
Finalize Reliable Implementation | 17 | 5 | 36 | 6 | 0% | bar: Apr 17 to May 21
Jarrod Sweeney
Activity 22 | 14 | 7 | 14 | 3 | 0%
Activity 23 | 15 | 4 | 15 | 8 | 12%
Activity 24 | 15 | 5 | 15 | 3 | 5%
Activity 25 | 15 | 8 | 15 | 5 | 0%
Activity 26 | 16 | 28 | 16 | 30 | 50%
Activity 27
Activity 28
Activity 29
Activity 30
Chandler Miles
Activity 32
Activity 33
Activity 34
Activity 35
Activity 36
Activity 37
Activity 38
Activity 39
Activity 40
Zach McKie
Activity 42
Activity 43
Activity 44
Activity 45
Activity 46
Activity 47
Activity 48
Activity 49
Activity 50
Activity 51
Activity 52
Activity 53
Activity 54
Activity 55
Activity 56
Activity 57
Activity 58
Activity 59
Activity 60
Activity 61